IB-040618r2.1-10p

Instructions on Using DAGS Inspection Branch Forms – June 18, 2004

- Submittal Register:

- Contractor shall prepare the submittal register.

- All submittals required by specifications shall be listed in the register, including all required tests and closing documents.

- Contractor shall keep the register updated including sent and receive dates and approval codes.

- There are basically three categories of submittals; Data, Testing, and Closing

- List each type of item in a section as a separate line item

- The updated register shall be emailed to Inspection Branch and the design consultant upon request.  An updated register will be required prior to processing any monthly payment.

You may add rows to the Excel spreadsheet, but do not add columns or make other modifications.  Use of the form must remain uniform.

- Submittal Transmittal:

Standard Procedure:

- Contractor shall prepare the submittal transmittal.

- All submittals shall have the proper amount of copies.  State (2), Consultant (2), User (1)

- A transmittal with Contractor’s stamp is attached.

- Contractor shall sign and date the first signature line.

- Contractor shall deliver the submittal to DAGS Inspection Branch.

- Inspection Branch shall sign and date the second line on the transmittal, and notify the Consultant to pick up submittal.

- Consultant shall review submittal, attach their stamp with code, then sign and date the third line on the transmittal.  Any comments may be attached to a separate transmittal or made directly on the submittal.  Consultant may retain one or two copies, depending if a sub consultant is involved.

- Consultant shall deliver the submittal to Inspection Branch.

- Inspection Branch will sign and date the fourth line on the transmittal and notify the contractor to pick up the submittal.

No submittal will be considered approved unless it has been signed by Inspection Branch.

STATE OF HAWAII

DEPARTMENT OF ACCOUNTING AND GENERAL SERVICES

DIVISION OF PUBLIC WORKS

P.O. BOX 119

HONOLULU, HAWAII  96810-0119

TRANSMITTAL FORM

| PROJECT: | LOCATION |
| --- | --- |
|  | WHERE & WHAT IS BEING DONE |
| D.A.G.S. JOB NO: |  |
| PROJECT ENGINEER: |  | INSPECTOR: |  |
| CONTRACTOR | CONTRACTOR NAME |  | CONSULTANT | LEAD CONSULTANT NAME |
| PHONE: |  |  | PHONE: |  |
| FAX: |  |  | FAX: |  |
| EMAIL: |  |  | EMAIL: |  |
| TRANSMITTAL TYPE: |
| SUBMITTAL | X | REQUEST FOR CHANGE (RFC) |  | MONTHLY ESTIMATE |  |
| PAYROLL AFFADAVIT |  | REPORT |  |
|  | INFORMATION |  |
| NO. | DATE SENT | NO. SENT | SECTION NO. / REF. | SECTION NAME | ITEM SENT | TYPE | *NO. RTN’D | ** CODE |
| * | COPIES RETURNED TO THE CONTRACTOR AFTER 2 OR 3 COPIES TO THE STATE | ** | SUBMITTAL COMPLETION CODE - BELOW: |
| A01 | Approved, Subject to Contract Requirements | D01 | Disapproved, Not pre-qualified |
| A02 | Approved as Noted, Subject to Contract Requirements | D02 | Resubmitted and Disapproved |
| A03 | Resubmitted and Approved | R01 | Disapproved, Revise and Resubmit |
|  | I01 | For your reference |
|  |  | <<Note if sent directly to the Consultant |
| SIGN – CONTRACTOR SENDING TRANSMITTAL |  | DATE |  | If arranged - Consultant to retain own copies & return 2 copies to DAGS. Contractor to pick-up the << rest. |
| SIGN - RECEIVED FROM CONTRACTOR - SENT TO CONSULTANT |  | DATE |  |  |
| SIGN - CONSULTANT RECEIVES & REVIEWED |  | DATE |  |  |
| SIGN - RECEIVED FROM CONSULTANT - SENT TO CONTRACTOR |  | DATE |  |  |
| REMARKS: |

| CONTRACTOR NAME |
| --- |
| PROJECT: |  |
| DAGS JOB NO. |  |
| THIS SUBMITTAL HAS BEEN CHECKED BY THIS GENERAL CONTRACTOR. IT IS CERTIFIED CORRECT, COMPLETE, AND IN COMPLIANCE WITH CONTRACT DRAWINGS AND SPECIFICATIONS. ALL AFFECTED CONTRACTORS AND SUPPLIERS ARE AWARE OF, AND WILL INTEGRATE THIS SUBMITTAL INTO THEIR OWN WORK. |
| SUBMITTAL NUMBER…………….. |  |
| DATE RECEIVED…………………… |  |
| SPECIFICATION SECTION NO…… |  |
| SPECIFICATION PARAGRAPH NO. |  |
| DRAWING NUMBER………………. |  |
| SUBCONTRACTOR NAME………… |  |
| SUPPLIER NAME…………………… |  |
| MANUFACTURER NAME…………. |  |
| NOTE: DEVIATIONS FROM THE CONTRACT DOCUMENTS ARE PROPOSED AS FOLLOWS |
|  | DEVIATION |  | NONE |
| DEVIATION BEING INCORPORATED: |
| CERTIFIED BY: |  | DATE: |  |

Alternative Procedure 1:

- In order to expedite processing of submittals, with Inspections Branch’s specific approval, the Contractor may deliver the submittal package directly to the consultant and shall check the box on the mid-right side of the form, indicating this is being done.

- Upon the Consultant completing their review of the submittal, signing and approval coding it, the Contractor can pick-up and deliver the submittal to Inspection Branch; or the Consultant shall deliver the package to Inspection Branch.

- Inspection Branch will sign and date the fourth line on the transmittal and notify the contractor to pick up the submittal.

No submittal will be considered approved unless it has been signed by Inspection Branch.

Alternative Procedure 2:

Submittals may be emailed without hand carrying of any documents or paperless.

- Inspection Branch, Contractor, and Consultant must be in agreement and each must have the capability before proceeding with emailing of submittals, though this capability should be reached by all parties within a year.

- The entire package, including the Transmittal Form (in MS WORD with digital signature), Contractor/Consultant Stamp (in MS WORD) – see below, and Submittal data (.pdf) are sent to the Consultant and Inspection Branch simultaneously.

| ( CONTRACTOR NAME & ICON ) |
| --- |
| PROJECT: |  |
| DAGS JOB NO. |  |
| THIS SUBMITTAL HAS BEEN CHECKED BY THIS GENERAL CONTRACTOR. IT IS CERTIFIED CORRECT, COMPLETE, AND IN COMPLIANCE WITH CONTRACT DRAWINGS AND SPECIFICATIONS. ALL AFFECTED CONTRACTORS AND SUPPLIERS ARE AWARE OF, AND WILL INTEGRATE THIS SUBMITTAL INTO THEIR OWN WORK. |
| SUBMITTAL NUMBER…………….. |  |
| DATE RECEIVED…………………… |  |
| SPECIFICATION SECTION NO…… |  |
| SPECIFICATION PARAGRAPH NO. |  |
| DRAWING NUMBER………………. |  |
| SUBCONTRACTOR NAME………… |  |
| SUPPLIER NAME…………………… |  |
| MANUFACTURER NAME…………. |  |
| NOTE: DEVIATIONS FROM THE CONTRACT DOCUMENTS ARE PROPOSED AS FOLLOWS |
|  | DEVIATION |  | NONE |
| DEVIATION BEING INCORPORATED: |
| CERTIFIED BY: |  | DATE: |  |

|  | NO EXCEPTIONS TAKEN |  | REJECTED – SEE REMARKS |
| --- | --- | --- | --- |
|  | MAKE CORRECTIONS NOTED |  | FURNISH AS SUBMITTED |
|  | AMEND AND RESUBMIT |  | SUBMIT SPECIFIED ITEM |
| Corrections or comments made on the shop drawings during this review do not relieve the contractor from compliance with requirement of the drawings and specifications. This check is only for review of general conformance with the design concept of the contract documents. The contractor is responsible for confirming and correlating all quantities and dimensions; selecting fabrication processes and techniques of construction; coordinating his work with that of all trades; and performing his work in a safe and satisfactory manner. |
| Date: |  | By: |  |
| (CONSULTANT LOGO/ICON AND/OR NAME) |
| REMARKS: |

- Should it be agreed upon, the Contractor can send the Contractor/Consultant stamp.  The Contractor & Consultant should redo the appropriate stamp to their specifications, including adding their own icon.  Should there be comments by the Consultant, they may be made at the bottom of the stamp.

- The Transmittal Form shall be sent back in its original format so Inspection Branch can sign, pdf, and distribute.  The Contractor/Consultant stamps can be returned to Inspection Branch in their original form or in pdf.

- Shop Drawings shall be sent in .DWG or pdf formats only

No submittal will be considered approved unless it has been signed by Inspection Branch.

3.   Request for Information (RFI):

| REQUEST FOR INFORMATION |
| --- |
|  | DATE |  |
|  | RFI NO. |  |
| DESCRIPTION |  |
| PROJECT : |  |
| DAGS JOB NO. |  |
| CONTRACTOR: |  | CONSULTANT: |  |
| TYPE OF REQUEST: | CLARIFY |  | CONFLICT |  | DISCREPANCY |  | SUGGEST |  | OTHER |  |
| PROBLEM: |  |
| WHERE? |  |
| COST: | $ |
| ATTACHMENTS |  |
| CONTRACTOR - SEND COPIES TO DAGS & CONSULTANT |
| SOLUTION |  |
| CONSULTANT/DAGS ESTIMATED COST | $ |
| ATTACHMENTS |  |
| CONSULTANT - SEND COPIES BACK TO DAGS & CONTRACTOR |
| AREA ENGINEER |  | INSPECTOR |  |

This form is usually for Situation Clarification..

- Contractor shall complete the top half of the form, up to the shaded line stating, “CONTRACTOR – SEND….”

- Contractor shall email the form in MS WORD to Inspection Branch and the Design consultant for distribution.

- Consultant shall complete the next portion of the form up to the shaded line stating, “CONSULTANT – SEND….”

- Consultant shall email the form to Inspection Branch and the Consultant in MS WORD.

- Contractor shall not proceed with the work described on the form until the Contractor receives the form signed by Inspection Branch and only if there is no cost involved.

- Contractors shall send the RFI by in Word as an email attachment.

- Contractors shall take digital photos and send them as email attachments, as needed. This will determine if the Consultant will need to make a site visit..........

- Consultants shall review, add comments, and sent the response back to the Contractor and DAGS.  Consultants – Adding your pages to the cover sheet during the response will make the response more contiguous.

Should there be an added cost, but clarification is still needed no matter the solution, a very rough estimate should be included.  If a solution is known and obvious, then see Request for Change.  Any RFI involving extra will not be considered approved until it has been approved by Inspection Branch.

IF IT IS IMPORTANT TO YOU, DOWNLOAD &/OR PRINT A HARDCOPY FOR YOUR RECORDS and/or STORE ON OTHER MEDIA .......

Files could include, in sequence :

RFI & response – (REQ) – WORD Attachment to email – File Folder should be chronological

e.g. FILENAME : RFI_01_021302_WHERE TO PARK        - NORMAL

RFI_01r_021302_WHERE TO PARK      - REVISED

RFI_01R_021302_WHERE TO PARK     - RESPONSE

RFI_01r2R_021302_WHERE TO PARK - RESPONSE TO 2ND REVISION

RFI log –   See below

| REQUEST FOR INFORMATION (RFI) TRACKING LOG |
| --- |
| PROJECT: | WHERE: |  | WHAT: |  |
| DAGS JOB NO: | 22-22-9999 |  |
| RFI NO. | DATE SENT | DATE RESPND | NEED ADDED INFO | WHO? | PROBLEM | WHERE? | SOLUTION? | RESLV’D? | ANY COST ? |
| 1 |  |  |  |  |  |  |  |  |  |
| 2 |  |  |  |  |  |  |  |  |  |
| 3 |  |  |  |  |  |  |  |  |  |
| 4 |  |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  |  |  |  |  |  |
| 6 |  |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |  |  |

4.  Request for Change:

If the Contractor is aware of the need for a change to the contract plans or specifications and/or it is obvious that extra money will be required, the Contractor shall complete the Field Observation Form (RFC) and email it to Inspection Branch and the Prime Consultant.

- Contractor shall attach appropriate photos as needed to clearly explain the situation.  Forwarding unnecessary photos will delay Inspection Branch’s review of the problem.

- A ballpark estimated cost is required and must be inputted on the form..

The difference between the Request for Change and the Request for Information is that if the Contractor knows how to resolve a problem they may expedite the approval process by submitting the Request for Change form.  The information may be used in acquiring the Public Works Administrator’s approval to proceed with a change.  Do not proceed with any changes unless specifically directed by Inspection Branch in writing.  It is against the law to proceed with any change order if the funds are not available.

Who inputs the information on the form?

Option 1:

Inform Inspection Branch who will send someone to help gather the needed information.

Option 2:

Contractor doing and sending forward is the preferred method and will expedite the process.

Procedure to send RFI and getting a reply ... asking for & doing an RFC

To fill-out the Field Observation Form/RFC, answer the following:

- What is the problem? - Tell us what the problem is and/or what RFI this involves.

- What is the solution? - Tell us what the solution is and/or indicate what Consultant said (RFI)

- Where is the problem? - Give location by grid, plan page, photo, etc

- What is the estimated cost? - Ballpark, on-the-spot estimate unless a formal estimate is attached.

BOTTOM LINE:

  - To get ANY change order authorization, all the above data must be supplied, along with supporting evidence, and other internal information before it is sent forward to the State Engineer.

  - THERE IS NO GETTING AROUND IT.

  - Failure to supply any of the above  will only delay the process.

REQUEST FOR CHANGE - RFC

| CONTRACTOR: |  | Date: |  |
| --- | --- | --- | --- |
| CONTRACTOR’S CHANGE | Proposal No. |  |
| Project: |  |
|  | DAGS Job No.: |  |  |
| WHAT DOES THIS INVOLVE? |
|  | Geotechnical |  | Civil |  | Architect |  | Structural |  | Mechanical |
|  | Electrical |  | Asbestos/Lead/PCB |  | Other: |  |
| WHY HAS THIS COME UP? / WHO MISSED IT? |
|  | Customer Request - User to write request |
|  | Design Improvement - Consultant to write recommendation |
|  | Design Error |  | Design Omission |  | Contractor Error |  | Contractor Omission |
|  | Unforeseen Condition |  | Other: |  |
| WHERE IS THE PROBLEM LOCATED? - | What area - Building/Lot? What floor? What room? |
|  | Where in the room? What are the grid lines? |
| WHAT IS THE PROBLEM / RFI NO. IF APPLY? |
| WHAT IS YOUR RECOMMENDATION: |
| WHAT IS THE ESTIMATED COST: | $ |  |
| PHOTOS AND/OR SKETCHES: |

5.  Estimate for Change Order:

- Contractor shall submit any cost proposal using the estimate for change order form.

- The format of the estimate complies with the Interim General Conditions of the contract.

- All supporting estimates from subcontractors shall use this format.

- Suppliers estimates (no labor) need not use this form and can be lump sum.

- Consultants shall also use the form when an estimate for additional work is requested.

- All completed forms and additional data should be sent to Inspection Branch by email in pdf format.

For ALL extra work cost estimates requested by either a Field Order, Bulletin, or request from Inspection Branch in writing ( Letter or email), the Contractor will have to submit a quotation to Inspection Branch within 15 calendar days from notification, according to Section 4.3.3 – Duty of Contractor to Provide Proposal for Changes, of the Interim General Conditions 1999.  Extension of Time requests by the contractor caused by not adhering to this clause will not be allowed.

6.  Daily Reports:

- In order to keep more accurate records with better tracking for the Department and Industrial Relations, Daily Reports are required for each project.

- The Inspection Branch form is to be used by the General Contractor and all the project’s subcontractors each time work is done.

- You may use your own form as long as the information required has been approved by Inspection Branch.

| STATE OF HAWAII DEPARTMENT OF ACCOUNTING AND GENERAL SERVICES DIVISION OF PUBLIC WORKS – INSPECTION BRANCH PROJECT DAILY REPORT |
| --- |
| PROJECT: |  | REPORT NO.: |  |
|  |  | DATE: |  |
| DAGS JOB NO.: |  | DAY |  |
| CONTRACTOR: |  | STATE ENGINEER: |  |
| PROJECT MANAGER: |  | STATE INSPECTOR: |  |
| WEATHER: | CONDITION: |
|  | CLEAR |  | CLOUDY |  | RAIN |  | WINDY |  | DRY |  | DAMP |  | MUDDY |  | DUSTY |
| WORKMEN ON THE PROJECT |
| TRADE: |
|  | ENVIRONMENTAL |  | REINF. STEEL |  | CARPENTRY - RGH |  | DRYWALL |  | ELECTRICAL - EXT |
|  | LANDSCAPING |  | MASONARY |  | CARPENTRY - FIN |  | HARD TILE |  | ELECTRICAL - INT |
|  | GRADING |  | STRUCT. STL |  | ROOFING |  | FLOOR TILE/CARPET |  | FIRE SYSTEM |
|  | FOUNDATION - PILE |  |  |  | WATERPROOF |  | CEILING |  | ELEVATOR |
|  | FOUNDATION - REG |  |  |  | SHEETMETAL |  | AIR COND / VENT |  | BOILER |
|  |  |  |  |  | GLASS |  | PLUMBER |  |  |
| CLASSIFICATION: |  | NO. OF PEOPLE |  | TOTAL HOURS |  |
| WORK IN PROGRESS: |
| OBSERVED DEFECTIVE WORK: |
| OBSERVED CORRECTED WORK: |
| MATERIALS DELIVERED TODAY: |
| TESTING DONE TODAY: |
| QUESTIONS OR PROBLEMS: |
| REMARKS: |

Please contact the Inspection Branch Area Engineer or Architect in charge of the project should you have any questions concerning any of the above or for information on other available forms.

GENERAL :

- Everyone should have an email address with capability to transmit a minimum of 2 MB per transmission and 3 attachments.

- Minimize fax transmissions.

- Email attachment should be in either MS WORD, EXEL, or .pdf format.

- Best to make any pdf copies after signatures have been affixed.  Though conversion is possible, the Contractor, Consultant, DAGS, User would have copies to dispute forgeries.  A secure server or encryption may be called for in the future.

- Make a copy of all important transmissions to a hard drive or separate floppy, CD, or DVD disk.

WHAT ARE THE BASIC FORMS THAT YOU WILL NEED?

The essentials needed, currently include:

- Construction Commencement Requirements – Before starting Construction

- Submittal Register – Needed with first submittal

- Submittal Transmittal – Required for submittals, but for any use

- Contractors Submittal Stamp – Needed with all submittals.  With Consultant’s Approval stamp, if doing digitally.

- Request for Information – RFI – Used to clarify a point with or without money involved.

- Request for Change – RFC – Discrepancy requiring additional funds

- Daily Report – Data on progress and labor for all companies generating any labor.

- Daily Force Account – If requested to do a daily accounting of a change or field order

- Stored Goods – Needed to collect payment for material delivered off-site

- Daily Report – Needed daily by every company doing work on-site.  Minimum of weekly submission.  Electronically is preferred.

More forms could be added later without notice..

Other tracking and standard forms are available and can be sent to you by request.