## Instrctn
Revised Procedure for Submitting Copies of Contract Billings – 12/20
HELPFUL HINTS:
1. Sign signature in BLUE ink on the original copy to distinguish from the rest of the copies. Per auditor's instructions, the first copy must have an original signature. Copies have been returned when they felt that the original couldn'tt be distinguished from the copies.
2. Use a clip rather than staple to keep copies together in lieu of stapleing them.
3. CHECK RED NOTCH AT CORNER OF CELLS FOR HELPFUL HINTS
The order of the sheets should also be noted, so that the contractor does it correctly:
Monthly Estimate Sheet
Monthly Construction Progress Report (Basic)
Monthly Construction Progress Report (Change Order)
Basic Contract Retainage Sheet
Change Order Retainage Sheet
Statement of Contract Time
Graph - Show by Estimated Monthly progressIF linearly the Time vs Completion falls behind schedule
Monthly Progress Payments:
1. Contractor shall submit the following:
a. One complete original billing (monthly estimate, progress report, and statement of contract time)
b. Two copies of the monthly estimate sheet only
2. If corrections were necessary in processing the billing, forward a copy of the corrections to the contractor via email in PDF format. Instruct the contractor to “incorporate corrections into the next billing.”
3. If the project is for the University of Hawaii or Community Colleges, an additional copy of the complete billing shall be included when routing for processing and approval.
Retainage:
1. "Retained" shall be checked when a portion of the amount earned is withheld from the current monthly progress payment.
2. "Released" shall be checked when a portion or whole of the sum of retained from previous progress payments is
included in the current monthly progress payment.
Final Payments:
The process is the same as monthly progress payments except for the following:
1. Contractor shall submit the following:
a. One complete original
b. Two copies of the complete billing
c. Two copies of the monthly estimate sheet only
4. If the Project Acceptance date is on or before the current contract completion date, a statement of contract time is not required, however a notation on the monthly estimate should state “Proj Accept: (date), Contr Compl: (date).”
INSTRUCTIONS FOR FILLING-OUT THE MONTHLY ESTIMATE, MONTHLY PROGRESS REPORT WITH CHANGE ORDERS, AND STATEMENT OF CONTRACT TIME
1. We have tried to automate as much of the filling of the forms as possible.
2. Many, but not all of the repetitive items are linked. Please check the comments and try using the form.
3. Enter only the spaces shaded yellow. The forms are rather self-explanatory, if you check comments.
4. You are to submit only the amount of forms as needed.
5. The forms are made to record a total of 275 events which are usually only needed for larger projects or multiple building type projects.
6, MOST projects wlll use no more than the MONTHLY ESTIMATE, 1 each of the MONTHLY PROGRESS REPORT and CHANGE ORDER SHEET - as needed, and the STATEMENT OF CONTRACT TIME.
7. Follow the directions above as to the amount of copies of each to submit, and when.
8. May not be fully debugged.
9. Double check work by own methods
CHANGES OF NOTE:
MONTHLY ESTIMATE:
1. There is only one entry for Change Orders. This is for approved TOTAL ONLY.
MONTHLY PROGRESS REPORT:
1. This sheet(s) have the SAME entries as for the submitted Construction Schedule & the Cost Breakdown submitted for the Commencement Requirements for the project.
2. As most projects do not need it, most contracts will use no more than the first sheet (35 events), or only one sheet will be submitted monthly.
3. Should any project require more than 275 events, submittals excluded, then a new worksheet will have to be pasted.
STATEMENT OF CONTRACT TIME:
1. There is only one sheet needed as opposed to one sheet per month. All time is now measured in calendar days. The only time another sheet is needed is if the project is more than a year in duration
2. More than one sheet will be needed only if the contract should extend more than a year, then a new worksheet will have to be pasted.

## MNTHLY EST
FORM DPW-CIA 2/05 |  | STATE OF HAWAII
Department of Accounting and General Services
Division of Public Works
MONTHLY ESTIMATE
|  |  |  | FOR THE MONTH OF |  |  | DECEMBER 2020
[7 empty] | Date: | 2020-12-01
CONTRACTOR: |  | Prime Contractor Name
ADDRESS: | [5 empty] | Contract No. |  |  | XXXXX | [ ]
City, State ZIP: |  |  |  |  | DAGS Job No. |  |  | XX-XX-XXXX
PROJECT TITLE: |  | Aliiaimoku Bldg, Replace Air Conditioning System
CONTRACT | [5 empty] | FOR CONSTRUCTION MANAGEMENT BRANCH USE
[ ] SUBMITTAL REGISTER [ ] COMMENCEMENT REQUIREMENTS
Basic Contract Amount |  |  | 1904000 |  |  | DUE MONTHLY: |  | [ ] PROJECT SCHEDULE
[ ] DAILY REPORTS [ ] PAYROLL AFFIDAVITS
[6 empty] | MONTHLY ESTIMATE CHECKLIST |  |  | [ ] CONTRACT NUMBER
[ ] PROJECT NAME AND LOCATION [ ] ALL SIGNATURES [ ] AS NEED - WASTE REDUCTION PROGRESS REPORT
CHANGE ORDERS | [5 empty] | SPECIALTY / MISC:
Total | 122832 |  |  |  |  | [ ] AIR CONDITION ACCEPTANCE [ ] PAINT ACCEPTANCE
Adjusted Contract Amount |  |  | 2026832
WORK ACCOMPLISHED |  |  |  | Basic Contract |  |  | Change Order |  | Total
Completed to Date |  |  | 16.79% | 319731 |  | 100% | 122832 |  | 442563
Retained [ ] RELEASED [ ] |  |  |  | 15986 |  |  | 6141 |  | 22127
Amount Subject to Payment |  |  |  | 303745 |  |  | 116691 |  | 420436
Payments to Date |  |  |  | 250000 |  |  | 100000 |  | 350000
Payments Now Due |  |  |  | 53745 |  |  | 16691 |  | 70436
Payment No. FINAL [ ] |  |  | 18
Remarks: For projects already Accepted and/or Completed, delete Statement Of Contract Time and add.. [ ] Project Acceptance Date [ ] Project Completion Date |  |  | FOR OFFICE USE ONLY |  |  | 1. I certify that the above bill is correct, just, that payment has not been received, and all payroll affidavits have been submitted, are current, or proper deductive exclusions have been made to this request; and least 80% of our workforce resides in Hawaii. [ ] As a preferred contractor, I have submitted all apprenticeship approval forms.
2. Computed and Checked by:
I certify that all required insurance coverages have been in full force and effect for the entire period for which this payment is requested.
3. Recommended: |  | Project Inspector or Engineer |  | Date:
Name of Contractor
4. Recommended: |  | Area Engineer/Architect |  | Date:
5. Approved: |  | Branch Chief or District Engineer |  | Date: |  | By signature / Title: |  |  |  | Date
The Public Works Administrator certifies that change orders have been issued and the work performed.
|  | State Public Works Administrator |  | Date:
Note on E15: Automatic from MNTHLY PROG RPT1
Note on C20: AUTOMATIC FROM CHANGE ORDER SHEET
Note on F28: INSERT TOTAL EARNED UP TO LAST PAYMENT
Note on E25: INSERT VALUE. IF OTHER THAN 5% STANDARD, PUT IN REMARKS
Note on K10: CONTRACT OR PURCHASE ORDER NUMBER
Note on K11: INSERT DAGS JOB NO.
Note on K8: MONTH SPELLED, DATE, YEAR FORMAT
Note on D11: SELF-EXPLANATORY
Note on D10: SELF-EXPLANATORY
Note on E24: AUTOMATIC FROM MONTHLY PROGRESS REPORT
Note on E21: AUTOMATIC CALCULATED VALUE
Note on J6: INSERT AND AUTOMATIC TO ALL OTHER SHEETS
Note on L13: INSPECTOR TO DO MONTHLY CHECKLIST BELOW
Note on I25: INSERT VALUE. IF OTHER THAN 5% STANDARD, PUT IN REMARKS
Note on I24: AUTOMATIC FROM MONTHLY PROGRESS REPORT
Note on J24: AUTOMATIC FROM MONTHLY PROGRESS REPORT
Note on F26: jthirugn: Automatic from Basic Contract Retainage
Note on J26: jthirugn: Automatic from Change Order Retainage
Note on F24: jthirugn: Automatic from monthly progress report
Note on A47: NEW PWA ADVISORY FOR ASO AND PRE-AUDIT
Note on A26: Normally when project has been accepted and the State asks that the project be kept open for any number of reasons
Note on A30: CHECK IF THIS IS THE FINAL PAYMENT TO THE CONTRACTOR
Note on I31: Check for Preferred Contractor's Apprenticeship Training Monthly statement
Note on E32: If project has already been Accepted, forego the STATEMENT OF CONTRACT TIME and insert ACTUAL Accepted and/or Project Completion dates

## MNTHLY PROG RPT1
DPW FORM 60 |  |  |  |  | PAGE: | 1 | OF
STATE OF HAWAII
Department of Accounting and General Services Division of Public Works |  |  |  |  | FOR MONTH OF: | DECEMBER 2020
MONTHLY CONSTRUCTION PROGRESS REPORT |  |  |  |  | FOR PAYMENT NO.: |  | 18
PROJECT: Aliiaimoku Bldg, Replace Air Conditioning System | [5 empty] | Job#: XX-XX-XXXX
NO. (a) | DESCRIPTION OF ITEM (b) |  | TOTAL VALUE OF ITEM © | VALUE OF WORK COMPLETE/INSTALLED (d) [1] | VALUE OF MATERIALS DELIVERED (e) [2] | VALUE OF COMPLETE & DELIVERED (f)=(d)+(e) |  | PERCENT COMPLETE (g)
1 | Project Coordination/Administration |  | 169180 | 169180 | 0 | 169180 |  | 100%
2 | Bond, Permit, Insurance, Taxes |  | 46382 | 46382 |  | 46382 |  | 100%
3 | Mobilization/Construction Aids |  | 10800 | 10800 |  | 10800 |  | 100%
4 | Selective Demo (Concrete Coring - 02070) |  | 29700 | 29700 |  | 29700 |  | 100%
5 | Concrete/Reinforcement/Form (Aloha Steel |  | 24170 | 24170 |  | 24170 |  | 100%
6 | CMU Block (Aczon Construction Ltd. - 0422 |  | 5083 | 5083 |  | 5083 |  | 100%
7 | Structural Steel (S and M Weilding Co., Ltd. |  | 17768 | 17768 |  | 17768 |  | 100%
8 | Acoustical Ceiling (Ace Interiors - 09510) |  | 1988 | 1988 |  | 1988 |  | 100%
9 | Painting (Kikuta Painting - 09900) |  | 14660 | 14660 |  | 14660 |  | 100%
10 | Asbestos & Lead Removal (R&D Tech - 132 |  | 5500 | 0 |  | 0 |  | 0%
11 | Plumbing (Alco Mechanical - 15400) |  | 3138 | 0 |  | 0 |  | 0%
12 | AC & Ventilation/HVAC Cleaning (Standard |  | 1313611 | 0 |  | 0 |  | 0%
13 | Electrical (MK Electric - 16050, 16402 & 165 |  | 260000 | 0 |  | 0 |  | 0%
14 | Misc. Install/Carpentry Works |  | 2020 | 0 |  | 0 |  | 0%
15 | [5 empty] | 0 |  | #DIV/0!
16 | [5 empty] | 0 |  | #DIV/0!
17 | [5 empty] | 0 |  | #DIV/0!
18 | [5 empty] | 0 |  | #DIV/0!
19 | [5 empty] | 0 |  | #DIV/0!
20 | [5 empty] | 0 |  | #DIV/0!
21 | [5 empty] | 0 |  | #DIV/0!
22 | [5 empty] | 0 |  | #DIV/0!
23 | [5 empty] | 0 |  | #DIV/0!
24 | [5 empty] | 0 |  | #DIV/0!
25 | [5 empty] | 0 |  | #DIV/0!
26 | [5 empty] | 0 |  | #DIV/0!
27 | [5 empty] | 0 |  | #DIV/0!
28 | [5 empty] | 0 |  | #DIV/0!
29 | [5 empty] | 0 |  | #DIV/0!
30 | [5 empty] | 0 |  | #DIV/0!
31 | [5 empty] | 0 |  | #DIV/0!
32 | [5 empty] | 0 |  | #DIV/0!
33 | [5 empty] | 0 |  | #DIV/0!
34 | [5 empty] | 0 |  | #DIV/0!
35 | [5 empty] | 0 |  | #DIV/0!
1 | TOTAL FOR THIS SHEET [1] |  | 1904000 | 319731 | 0 | 319731 |  | 16.79%
2 | TOTAL FOR SHEET [2] |  | 0 | 0 | 0 | 0 |  | #DIV/0!
3 | TOTAL FOR SHEET [3] |  | 0 | 0 | 0 | 0 |  | #DIV/0!
4 | TOTAL FOR SHEET [4] |  | 0 | 0 | 0 | 0 |  | #DIV/0!
5 | TOTAL FOR SHEET [5] |  | 0 | 0 | 0 | 0 |  | #DIV/0!
| BASIC CONTRACT TOTALS: |  | 1904000 | 319731 | 0 | 319731 |  | 16.79%
TOOLS |  | WORK FORCE |  | PROGRESS |  | MATERIAL DELIVERY
SATISFACTORY |  | SATISFACTORY |  | SATISFACTORY |  | SATISFACTORY
[ ] YES [ ] NO |  | [ ] YES [ ] NO |  | [ ] YES [ ] NO |  | [ ] YES [ ] NO
[1] | Do not include payment for materials not incorporated in the work in this column. |  |  | I certify that the materials recommended for payment (1) have been delivered to the job site, (2) conform with specifications, (3) are stored in such a manner that they will not be afftected by the weather and/or elements, and (4) all phases of work are being satisfactorily pursued.
[2] | Use this column only for materials that have been [1] delivered and acceptably stored at the job site and [2] conform with the specifications. Amount shown should be 90% of the invoice value of such materials attached.
Project Inspector
Note on D8: VALUE OF THE DESCRIBED EVENT. INSERT THIS VALUE.
Note on E8: WORK THAT HAS BEEN INSTALLED ON THE SITE. INSERT THIS VALUE
Note on F8: MATERIAL DELIVERED, BUT NOT INSTALLED. 90% OF INVOICE SUBMITTED. INSERT THIS VALUE
Note on G8: WORK INSTALLED AND 90% OF MATERIALS AT THE SITE OR IN STORAGE. CALCUALTED VALUE
Note on I8: AMOUNT OF THE EVENT THAT IS COMPLETED. CALCULATED VALUE
Note on I1: TOTAL SHEETS INCLUDING CHANGE ORDER SHEET. ALL CELLS ARE LINKED
Note on H4: INSERT PAYMENT NUMBER REFERENCE
Note on B43: SUMMATIONS FOR COVER OR TALLY SHEET
Note on B44: SUMMATIONS FOR COVER OR TALLY SHEET
Note on B45: SUMMATIONS FOR COVER OR TALLY SHEET
Note on B46: SUMMATIONS FOR COVER OR TALLY SHEET
Note on B47: SUMMATIONS FOR COVER OR TALLY SHEET

## CHANGE ORDERS
DPW FORM 60 |  |  |  | PAGE: | CO1 | OF | 0
STATE OF HAWAII
Department of Accounting and General Services Division of Public Works |  |  |  | FOR MONTH OF: | DECEMBER 2020
MONTHLY CONSTRUCTION PROGRESS REPORT |  |  |  | FOR PAYMENT NO.: |  | 18
PROJECT: Aliiaimoku Bldg, Replace Air Conditioning System |  |  |  |  | Job#: XX-XX-XXXX
NO. (a) | DESCRIPTION OF CHANGE ORDER (b) | TOTAL VALUE OF ITEM © | VALUE OF WORK COMPLETE/INSTALLED (d) [1] | VALUE OF MATERIALS DELIVERED (e) [2] | VALUE OF COMPLETE & DELIVERED (f)=(d)+(e) |  | PERCENT COMPLETE (g)
1 | DAGS CO-01 | 4077 | 4077 | 0 | 4077 |  | 100%
2 | DAGS CO-02 Sound Barrier @ Temp Chiller | 5494 | 5494 |  | 5494 |  | 100%
3 | DAGS CO-03 | 5114 | 5114 |  | 5114 |  | 100%
4 | DAGS- CO-04/CP10 | 1768 | 1768 |  | 1768 |  | 100%
5 | DAGS CO-05/CP-12 | 14950 | 14950 |  | 14950 |  | 100%
6 | DAGS CO-06/CP-15 | 13102 | 13102 |  | 13102 |  | 100%
7 | DAGS CO-07/CP-16 | 1267 | 1267 |  | 1267 |  | 100%
8 | DAGS CO-08/CP-13 | 36970 | 36970 |  | 36970 |  | 100%
9 | DAGS--CO-09/CP-4, CP-8A | 22250 | 22250 |  | 22250 |  | 100%
10 | DAGS-CO-10/CP-11 | 3940 | 3940 |  | 3940 |  | 100%
11 | DAGS-CO-11/ | 13900 | 13900 |  | 13900 |  | 100%
12 |  |  |  |  | 0 |  | #DIV/0!
13 |  |  |  |  | 0 |  | #DIV/0!
14 |  |  |  |  | 0 |  | #DIV/0!
15 |  |  |  |  | 0 |  | #DIV/0!
16 |  |  |  |  | 0 |  | #DIV/0!
17 |  |  |  |  | 0 |  | #DIV/0!
18 |  |  |  |  | 0 |  | #DIV/0!
19 |  |  |  |  | 0 |  | #DIV/0!
20 |  |  |  |  | 0 |  | #DIV/0!
21 |  |  |  |  | 0 |  | #DIV/0!
22 |  |  |  |  | 0 |  | #DIV/0!
23 |  |  |  |  | 0 |  | #DIV/0!
24 |  |  |  |  | 0 |  | #DIV/0!
25 |  |  |  |  | 0 |  | #DIV/0!
26 |  |  |  |  | 0 |  | #DIV/0!
27 |  |  |  |  | 0 |  | #DIV/0!
28 |  |  |  |  | 0 |  | #DIV/0!
29 |  |  |  |  | 0 |  | #DIV/0!
30 |  |  |  |  | 0 |  | #DIV/0!
31 |  |  |  |  | 0 |  | #DIV/0!
32 |  |  |  |  | 0 |  | #DIV/0!
33 |  |  |  |  | 0 |  | #DIV/0!
34 |  |  |  |  | 0 |  | #DIV/0!
35 |  |  |  |  | 0 |  | #DIV/0!
36 |  |  |  |  | 0 |  | #DIV/0!
37 |  |  |  |  | 0 |  | #DIV/0!
38 |  |  |  |  | 0 |  | #DIV/0!
39 |  |  |  |  | 0 |  | #DIV/0!
40 |  |  |  |  | 0 |  | #DIV/0!
41 |  |  |  |  | 0 |  | #DIV/0!
42 |  |  |  |  | 0 |  | #DIV/0!
43 |  |  |  |  | 0 |  | #DIV/0!
44 |  |  |  |  | 0 |  | #DIV/0!
45 |  |  |  |  | 0 |  | #DIV/0!
46 |  |  |  |  | 0 |  | #DIV/0!
47 |  |  |  |  | 0 |  | #DIV/0!
48 |  |  |  |  | 0 |  | #DIV/0!
49 |  |  |  |  | 0 |  | #DIV/0!
50 |  |  |  |  | 0 |  | #DIV/0!
51 |  |  |  |  | 0 |  | #DIV/0!
52 |  |  |  |  | 0 |  | #DIV/0!
53 |  |  |  |  | 0 |  | #DIV/0!
54 |  |  |  |  | 0 |  | #DIV/0!
55 |  |  |  |  | 0 |  | #DIV/0!
56 |  |  |  |  | 0 |  | #DIV/0!
57 |  |  |  |  | 0 |  | #DIV/0!
58 |  |  |  |  | 0 |  | #DIV/0!
59 |  |  |  |  | 0 |  | #DIV/0!
60 |  |  |  |  | 0 |  | #DIV/0!
CO | CHANGE ORDER TOTALS | 122832 | 122832 | 0 | 122832 |  | 100%
Note on F8: MATERIAL DELIVERED, BUT NOT INSTALLED. 90% OF INVOICE SUBMITTED. INSERT THIS VALUE
Note on G8: WORK INSTALLED AND 90% OF MATERIALS AT THE SITE OR IN STORAGE. CALCUALTED VALUE
Note on I8: AMOUNT OF THE EVENT THAT IS COMPLETED. CALCULATED VALUE
Note on I1: TOTAL SHEETS SUBMITTED INCLUDING CHANGE ORDER. USUALLY 2 ONLY

## BASIC CONTRACT - RETAINAGE
DPW-CIA 7/06
BASIC CONTRACT - PRIME & SUB CONTRACTOR RETAINAGE CALCULATION
STATE OF HAWAII
Department of Accounting and General Services
Division of Public Works
| For the Month of: |  | DECEMBER 2020
| CONTRACTOR: | Prime Contractor Name |  |  |  | Contract No.: | XXXXX
| PROJECT TITLE: | Aliiaimoku Bldg, Replace Air Conditioning System |  |  |  | DAGS Job No.: | XX-XX-XXXX
CLOSED
| PRIME CONTRACTOR | TRADE | LICENSE NO. | BASIC CONTRACT AMOUNT | COMPL. TO DATE | % CMPL | RETN % | CONTRACT AMOUNT RETAINED
| Prime Contractor Name | General Contractor | ABC-23456 | 1779000 | 257231 | 14.46% | 5% | 12861 | A
| SUBCONTRACTOR | TRADE | LICENSE NO. | BASIC SUB-CONTRACT AMOUNT | COMPL. TO DATE | % CMPL | RETN % | SUB-CONTRACT AMOUNT RETAINED
| Sub A | Sealer | C-56789 | 100000 | 50000 | 50% | 5% | 2500
| Sub B | Landscape | C-7865 | 25000 | 12500 | 50% | 5% | 625
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
| Total Retained from Subs |  |  | 125000 | 62500 |  |  | 3125 | B
|  |  |  | 1904000 | 319731
| BASIC CONTRACT - RETAINED FROM PRIME AND SUBS (A+B) | [6 empty] | 15986
I certify that the above retentions are correct for this request.
Checked/Verified by:
Name of Contractor
Initial - Project Inspector or Engineer
By Signature Date
NOTE:
Columnar totals shall be equal in dollar value to that on the Monthly Estimate Sheet
Note on G13: Insert by GC per subcontr invoice agreement
Note on G19: Insert by GC per subcontr invoice agreement
Note on H19: Inserted by GC according to subcontract agreement
Note on I40: jthirugn: Amount retained from subs
Note on I45: jthirugn: Total amount retained from prime and subs
Note on H13: Inserted by GC according to subcontract agreement
Note on I15: jthirugn: Amount retained from prime.
Note on I21: jthirugn: Amount retained from prime.
Note on E42: jthirugn: Automatic from MNTHLY PROG RPT1
Note on F42: jthirugn: Automatic from MNTHLY PROG RPT1
Note on B15: jthirugn: Auto fill
Note on C9: jthirugn: Auto fill
Note on E15: Gross amount without subcontractor amount
Note on F15: Gross complete without subcontractor amount

## CHANGE ORDER - RETAINAGE
DPW-CIA 7/06
CHANGE ORDER - PRIME & SUB CONTRACTOR RETAINAGE CALCULATION
STATE OF HAWAII
Department of Accounting and General Services
Division of Public Works
| For the Month of: |  | DECEMBER 2020
| CONTRACTOR: | Prime Contractor Name |  |  |  | Contract No.: | XXXXX
| PROJECT TITLE: | Aliiaimoku Bldg, Replace Air Conditioning System |  |  |  | DAGS Job No.: | XX-XX-XXXX
CLOSED
| PRIME CONTRACTOR | TRADE | LICENSE NO. | CHANGE ORDER AMOUNT | COMPL. TO DATE | % CMPL | RETN % | CHANGE ORDER AMOUNT RETAINED
| Prime Contractor Name | General Contractor | ABC-23456 | 107832 | 107832 | 100% | 5% | 5391 | A
| SUBCONTRACTOR | TRADE | LICENSE NO. | CHANGE ORDER SUB AMOUNT | COMPL. TO DATE | % CMPL | RETN % | CHANGE ORDER SUB AMOUNT RETAINED
| Sub A | Sealer | C-56789 | 10000 | 10000 | 100% | 5% | 500
| Sub B | Landscape | C-7865 | 5000 | 5000 | 100% | 5% | 250
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
[6 empty] | #DIV/0! | 5% | 0
| Total Retained from Subs |  |  | 15000 | 15000 |  |  | 750 | B
|  |  |  | 122832 | 122832
| CHANGE ORDER CONTRACT - RETAINED FROM PRIME AND SUBS (A+B) | [6 empty] | 6141
I certify that the above retentions are correct for this request.
Checked/Verified by:
Name of Contractor
Initial - Project Inspector or Engineer
By Signature Date
NOTE:
Columnar totals shall be equal in dollar value to that on the Monthly Estimate Sheet
Note on G13: Insert by GC per subcontr invoice agreement
Note on G19: Insert by GC per subcontr invoice agreement
Note on H19: Inserted by GC according to subcontract agreement
Note on I40: jthirugn: Amount retained from subs
Note on I45: jthirugn: Total amount retained from prime and subs
Note on H13: Inserted by GC according to subcontract agreement
Note on I15: jthirugn: Amount retained from prime.
Note on I21: jthirugn: Amount retained from prime.
Note on E42: jthirugn: Automatic from change orders
Note on F42: jthirugn: Automatic from change orders
Note on C9: jthirugn: Auto fill
Note on B15: jthirugn: Auto fill
Note on E15: Gross minus subcontractor portion
Note on F15: Gross minus subcontractor portion

## MNTHLY PROG RPT1 (2)
DPW FORM 60 |  |  |  | PAGE: | 2 | OF | 0
STATE OF HAWAII
Department of Accounting and General Services Division of Public Works |  |  |  | FOR MONTH OF: | DECEMBER 2020
MONTHLY CONSTRUCTION PROGRESS REPORT |  |  |  | FOR PAYMENT NO.: |  | 18
PROJECT: Aliiaimoku Bldg, Replace Air Conditioning System |  |  |  |  | Job#: XX-XX-XXXX
NO. (a) | DESCRIPTION OF ITEM (b) | TOTAL VALUE OF ITEM © | VALUE OF WORK COMPLETE/INSTALLED (d) [1] | VALUE OF MATERIALS DELIVERED (e) [2] | VALUE OF COMPLETE & DELIVERED (f)=(d)+(e) |  | PERCENT COMPLETE (g)
36 |  | 0 | 0 | 0 | 0 |  | #DIV/0!
37 |  |  |  |  | 0 |  | #DIV/0!
38 |  |  |  |  | 0 |  | #DIV/0!
39 |  |  |  |  | 0 |  | #DIV/0!
40 |  |  |  |  | 0 |  | #DIV/0!
41 |  |  |  |  | 0 |  | #DIV/0!
42 |  |  |  |  | 0 |  | #DIV/0!
43 |  |  |  |  | 0 |  | #DIV/0!
44 |  |  |  |  | 0 |  | #DIV/0!
45 |  |  |  |  | 0 |  | #DIV/0!
46 |  |  |  |  | 0 |  | #DIV/0!
47 |  |  |  |  | 0 |  | #DIV/0!
48 |  |  |  |  | 0 |  | #DIV/0!
49 |  |  |  |  | 0 |  | #DIV/0!
50 |  |  |  |  | 0 |  | #DIV/0!
51 |  |  |  |  | 0 |  | #DIV/0!
52 |  |  |  |  | 0 |  | #DIV/0!
53 |  |  |  |  | 0 |  | #DIV/0!
54 |  |  |  |  | 0 |  | #DIV/0!
55 |  |  |  |  | 0 |  | #DIV/0!
56 |  |  |  |  | 0 |  | #DIV/0!
57 |  |  |  |  | 0 |  | #DIV/0!
58 |  |  |  |  | 0 |  | #DIV/0!
59 |  |  |  |  | 0 |  | #DIV/0!
60 |  |  |  |  | 0 |  | #DIV/0!
61 |  |  |  |  | 0 |  | #DIV/0!
62 |  |  |  |  | 0 |  | #DIV/0!
63 |  |  |  |  | 0 |  | #DIV/0!
64 |  |  |  |  | 0 |  | #DIV/0!
65 |  |  |  |  | 0 |  | #DIV/0!
66 |  |  |  |  | 0 |  | #DIV/0!
67 |  |  |  |  | 0 |  | #DIV/0!
68 |  |  |  |  | 0 |  | #DIV/0!
69 |  |  |  |  | 0 |  | #DIV/0!
70 |  |  |  |  | 0 |  | #DIV/0!
71 |  |  |  |  | 0 |  | #DIV/0!
72 |  |  |  |  | 0 |  | #DIV/0!
73 |  |  |  |  | 0 |  | #DIV/0!
74 |  |  |  |  | 0 |  | #DIV/0!
75 |  |  |  |  | 0 |  | #DIV/0!
76 |  |  |  |  | 0 |  | #DIV/0!
77 |  |  |  |  | 0 |  | #DIV/0!
78 |  |  |  |  | 0 |  | #DIV/0!
79 |  |  |  |  | 0 |  | #DIV/0!
80 |  |  |  |  | 0 |  | #DIV/0!
81 |  |  |  |  | 0 |  | #DIV/0!
82 |  |  |  |  | 0 |  | #DIV/0!
83 |  |  |  |  | 0 |  | #DIV/0!
84 |  |  |  |  | 0 |  | #DIV/0!
85 |  |  |  |  | 0 |  | #DIV/0!
86 |  |  |  |  | 0 |  | #DIV/0!
87 |  |  |  |  | 0 |  | #DIV/0!
88 |  |  |  |  | 0 |  | #DIV/0!
89 |  |  |  |  | 0 |  | #DIV/0!
90 |  |  |  |  | 0 |  | #DIV/0!
91 |  |  |  |  | 0 |  | #DIV/0!
92 |  |  |  |  | 0 |  | #DIV/0!
93 |  |  |  |  | 0 |  | #DIV/0!
94 |  |  |  |  | 0 |  | #DIV/0!
95 |  |  |  |  | 0 |  | #DIV/0!
2 | TOTAL FOR THIS SHEET [2] | 0 | 0 | 0 | 0 |  | #DIV/0!
Note on D8: VALUE OF THE DESCRIBED EVENT. INSERT THIS VALUE.
Note on E8: WORK THAT HAS BEEN INSTALLED ON THE SITE. INSERT THIS VALUE
Note on F8: MATERIAL DELIVERED, BUT NOT INSTALLED. 90% OF INVOICE SUBMITTED. INSERT THIS VALUE
Note on G8: WORK INSTALLED AND 90% OF MATERIALS AT THE SITE OR IN STORAGE. CALCUALTED VALUE
Note on I8: AMOUNT OF THE EVENT THAT IS COMPLETED. CALCULATED VALUE

## MNTHLY PROG RPT1 (3)
DPW FORM 60 |  |  |  | PAGE: | 3 | OF | 0
STATE OF HAWAII
Department of Accounting and General Services Division of Public Works |  |  |  | FOR MONTH OF: | DECEMBER 2020
MONTHLY CONSTRUCTION PROGRESS REPORT |  |  |  | FOR PAYMENT NO.: |  | 18
PROJECT: Aliiaimoku Bldg, Replace Air Conditioning System |  |  |  |  | Job#: XX-XX-XXXX
NO. (a) | DESCRIPTION OF ITEM (b) | TOTAL VALUE OF ITEM © | VALUE OF WORK COMPLETE/INSTALLED (d) [1] | VALUE OF MATERIALS DELIVERED (e) [2] | VALUE OF COMPLETE & DELIVERED (f)=(d)+(e) |  | PERCENT COMPLETE (g)
96 |  | 0 | 0 | 0 | 0 |  | #DIV/0!
97 |  |  |  |  | 0 |  | #DIV/0!
98 |  |  |  |  | 0 |  | #DIV/0!
99 |  |  |  |  | 0 |  | #DIV/0!
100 |  |  |  |  | 0 |  | #DIV/0!
101 |  |  |  |  | 0 |  | #DIV/0!
102 |  |  |  |  | 0 |  | #DIV/0!
103 |  |  |  |  | 0 |  | #DIV/0!
104 |  |  |  |  | 0 |  | #DIV/0!
105 |  |  |  |  | 0 |  | #DIV/0!
106 |  |  |  |  | 0 |  | #DIV/0!
107 |  |  |  |  | 0 |  | #DIV/0!
108 |  |  |  |  | 0 |  | #DIV/0!
109 |  |  |  |  | 0 |  | #DIV/0!
110 |  |  |  |  | 0 |  | #DIV/0!
111 |  |  |  |  | 0 |  | #DIV/0!
112 |  |  |  |  | 0 |  | #DIV/0!
113 |  |  |  |  | 0 |  | #DIV/0!
114 |  |  |  |  | 0 |  | #DIV/0!
115 |  |  |  |  | 0 |  | #DIV/0!
116 |  |  |  |  | 0 |  | #DIV/0!
117 |  |  |  |  | 0 |  | #DIV/0!
118 |  |  |  |  | 0 |  | #DIV/0!
119 |  |  |  |  | 0 |  | #DIV/0!
120 |  |  |  |  | 0 |  | #DIV/0!
121 |  |  |  |  | 0 |  | #DIV/0!
122 |  |  |  |  | 0 |  | #DIV/0!
123 |  |  |  |  | 0 |  | #DIV/0!
124 |  |  |  |  | 0 |  | #DIV/0!
125 |  |  |  |  | 0 |  | #DIV/0!
126 |  |  |  |  | 0 |  | #DIV/0!
127 |  |  |  |  | 0 |  | #DIV/0!
128 |  |  |  |  | 0 |  | #DIV/0!
129 |  |  |  |  | 0 |  | #DIV/0!
130 |  |  |  |  | 0 |  | #DIV/0!
131 |  |  |  |  | 0 |  | #DIV/0!
132 |  |  |  |  | 0 |  | #DIV/0!
133 |  |  |  |  | 0 |  | #DIV/0!
134 |  |  |  |  | 0 |  | #DIV/0!
135 |  |  |  |  | 0 |  | #DIV/0!
136 |  |  |  |  | 0 |  | #DIV/0!
137 |  |  |  |  | 0 |  | #DIV/0!
138 |  |  |  |  | 0 |  | #DIV/0!
139 |  |  |  |  | 0 |  | #DIV/0!
140 |  |  |  |  | 0 |  | #DIV/0!
141 |  |  |  |  | 0 |  | #DIV/0!
142 |  |  |  |  | 0 |  | #DIV/0!
143 |  |  |  |  | 0 |  | #DIV/0!
144 |  |  |  |  | 0 |  | #DIV/0!
145 |  |  |  |  | 0 |  | #DIV/0!
146 |  |  |  |  | 0 |  | #DIV/0!
147 |  |  |  |  | 0 |  | #DIV/0!
148 |  |  |  |  | 0 |  | #DIV/0!
149 |  |  |  |  | 0 |  | #DIV/0!
150 |  |  |  |  | 0 |  | #DIV/0!
151 |  |  |  |  | 0 |  | #DIV/0!
152 |  |  |  |  | 0 |  | #DIV/0!
153 |  |  |  |  | 0 |  | #DIV/0!
154 |  |  |  |  | 0 |  | #DIV/0!
155 |  |  |  |  | 0 |  | #DIV/0!
3 | TOTAL FOR THIS SHEET [3] | 0 | 0 | 0 | 0 |  | #DIV/0!
Note on D8: VALUE OF THE DESCRIBED EVENT. INSERT THIS VALUE.
Note on E8: WORK THAT HAS BEEN INSTALLED ON THE SITE. INSERT THIS VALUE
Note on F8: MATERIAL DELIVERED, BUT NOT INSTALLED. 90% OF INVOICE SUBMITTED. INSERT THIS VALUE
Note on G8: WORK INSTALLED AND 90% OF MATERIALS AT THE SITE OR IN STORAGE. CALCUALTED VALUE
Note on I8: AMOUNT OF THE EVENT THAT IS COMPLETED. CALCULATED VALUE

## MNTHLY PROG RPT1 (4)
DPW FORM 60 |  |  |  | PAGE: | 4 | OF | 0
STATE OF HAWAII
Department of Accounting and General Services Division of Public Works |  |  |  | FOR MONTH OF: | DECEMBER 2020
MONTHLY CONSTRUCTION PROGRESS REPORT |  |  |  | FOR PAYMENT NO.: |  | 18
PROJECT: Aliiaimoku Bldg, Replace Air Conditioning System |  |  |  |  | Job#: XX-XX-XXXX
NO. (a) | DESCRIPTION OF ITEM (b) | TOTAL VALUE OF ITEM © | VALUE OF WORK COMPLETE/INSTALLED (d) [1] | VALUE OF MATERIALS DELIVERED (e) [2] | VALUE OF COMPLETE & DELIVERED (f)=(d)+(e) |  | PERCENT COMPLETE (g)
156 |  | 0 | 0 | 0 | 0 |  | #DIV/0!
157 |  |  |  |  | 0 |  | #DIV/0!
158 |  |  |  |  | 0 |  | #DIV/0!
159 |  |  |  |  | 0 |  | #DIV/0!
160 |  |  |  |  | 0 |  | #DIV/0!
161 |  |  |  |  | 0 |  | #DIV/0!
162 |  |  |  |  | 0 |  | #DIV/0!
163 |  |  |  |  | 0 |  | #DIV/0!
164 |  |  |  |  | 0 |  | #DIV/0!
165 |  |  |  |  | 0 |  | #DIV/0!
166 |  |  |  |  | 0 |  | #DIV/0!
167 |  |  |  |  | 0 |  | #DIV/0!
168 |  |  |  |  | 0 |  | #DIV/0!
169 |  |  |  |  | 0 |  | #DIV/0!
170 |  |  |  |  | 0 |  | #DIV/0!
171 |  |  |  |  | 0 |  | #DIV/0!
172 |  |  |  |  | 0 |  | #DIV/0!
173 |  |  |  |  | 0 |  | #DIV/0!
174 |  |  |  |  | 0 |  | #DIV/0!
175 |  |  |  |  | 0 |  | #DIV/0!
176 |  |  |  |  | 0 |  | #DIV/0!
177 |  |  |  |  | 0 |  | #DIV/0!
178 |  |  |  |  | 0 |  | #DIV/0!
179 |  |  |  |  | 0 |  | #DIV/0!
180 |  |  |  |  | 0 |  | #DIV/0!
181 |  |  |  |  | 0 |  | #DIV/0!
182 |  |  |  |  | 0 |  | #DIV/0!
183 |  |  |  |  | 0 |  | #DIV/0!
184 |  |  |  |  | 0 |  | #DIV/0!
185 |  |  |  |  | 0 |  | #DIV/0!
186 |  |  |  |  | 0 |  | #DIV/0!
187 |  |  |  |  | 0 |  | #DIV/0!
188 |  |  |  |  | 0 |  | #DIV/0!
189 |  |  |  |  | 0 |  | #DIV/0!
190 |  |  |  |  | 0 |  | #DIV/0!
191 |  |  |  |  | 0 |  | #DIV/0!
192 |  |  |  |  | 0 |  | #DIV/0!
193 |  |  |  |  | 0 |  | #DIV/0!
194 |  |  |  |  | 0 |  | #DIV/0!
195 |  |  |  |  | 0 |  | #DIV/0!
196 |  |  |  |  | 0 |  | #DIV/0!
197 |  |  |  |  | 0 |  | #DIV/0!
198 |  |  |  |  | 0 |  | #DIV/0!
199 |  |  |  |  | 0 |  | #DIV/0!
200 |  |  |  |  | 0 |  | #DIV/0!
201 |  |  |  |  | 0 |  | #DIV/0!
202 |  |  |  |  | 0 |  | #DIV/0!
203 |  |  |  |  | 0 |  | #DIV/0!
204 |  |  |  |  | 0 |  | #DIV/0!
205 |  |  |  |  | 0 |  | #DIV/0!
206 |  |  |  |  | 0 |  | #DIV/0!
207 |  |  |  |  | 0 |  | #DIV/0!
208 |  |  |  |  | 0 |  | #DIV/0!
209 |  |  |  |  | 0 |  | #DIV/0!
210 |  |  |  |  | 0 |  | #DIV/0!
211 |  |  |  |  | 0 |  | #DIV/0!
212 |  |  |  |  | 0 |  | #DIV/0!
213 |  |  |  |  | 0 |  | #DIV/0!
214 |  |  |  |  | 0 |  | #DIV/0!
215 |  |  |  |  | 0 |  | #DIV/0!
4 | TOTAL FOR THIS SHEET [4] | 0 | 0 | 0 | 0 |  | #DIV/0!
Note on D8: VALUE OF THE DESCRIBED EVENT. INSERT THIS VALUE.
Note on E8: WORK THAT HAS BEEN INSTALLED ON THE SITE. INSERT THIS VALUE
Note on F8: MATERIAL DELIVERED, BUT NOT INSTALLED. 90% OF INVOICE SUBMITTED. INSERT THIS VALUE
Note on G8: WORK INSTALLED AND 90% OF MATERIALS AT THE SITE OR IN STORAGE. CALCUALTED VALUE
Note on I8: AMOUNT OF THE EVENT THAT IS COMPLETED. CALCULATED VALUE

## MNTHLY PROG RPT1 (5)
DPW FORM 60 |  |  |  | PAGE: | 5 | OF | 0
STATE OF HAWAII
Department of Accounting and General Services Division of Public Works |  |  |  | FOR MONTH OF: | DECEMBER 2020
MONTHLY CONSTRUCTION PROGRESS REPORT |  |  |  | FOR PAYMENT NO.: |  | 18
PROJECT: Aliiaimoku Bldg, Replace Air Conditioning System |  |  |  |  | Job#: XX-XX-XXXX
NO. (a) | DESCRIPTION OF ITEM (b) | TOTAL VALUE OF ITEM © | VALUE OF WORK COMPLETE/INSTALLED (d) [1] | VALUE OF MATERIALS DELIVERED (e) [2] | VALUE OF COMPLETE & DELIVERED (f)=(d)+(e) |  | PERCENT COMPLETE (g)
216 |  | 0 | 0 | 0 | 0 |  | #DIV/0!
217 |  |  |  |  | 0 |  | #DIV/0!
218 |  |  |  |  | 0 |  | #DIV/0!
219 |  |  |  |  | 0 |  | #DIV/0!
220 |  |  |  |  | 0 |  | #DIV/0!
221 |  |  |  |  | 0 |  | #DIV/0!
222 |  |  |  |  | 0 |  | #DIV/0!
223 |  |  |  |  | 0 |  | #DIV/0!
224 |  |  |  |  | 0 |  | #DIV/0!
225 |  |  |  |  | 0 |  | #DIV/0!
226 |  |  |  |  | 0 |  | #DIV/0!
227 |  |  |  |  | 0 |  | #DIV/0!
228 |  |  |  |  | 0 |  | #DIV/0!
229 |  |  |  |  | 0 |  | #DIV/0!
230 |  |  |  |  | 0 |  | #DIV/0!
231 |  |  |  |  | 0 |  | #DIV/0!
232 |  |  |  |  | 0 |  | #DIV/0!
233 |  |  |  |  | 0 |  | #DIV/0!
234 |  |  |  |  | 0 |  | #DIV/0!
235 |  |  |  |  | 0 |  | #DIV/0!
236 |  |  |  |  | 0 |  | #DIV/0!
237 |  |  |  |  | 0 |  | #DIV/0!
238 |  |  |  |  | 0 |  | #DIV/0!
239 |  |  |  |  | 0 |  | #DIV/0!
240 |  |  |  |  | 0 |  | #DIV/0!
241 |  |  |  |  | 0 |  | #DIV/0!
242 |  |  |  |  | 0 |  | #DIV/0!
243 |  |  |  |  | 0 |  | #DIV/0!
244 |  |  |  |  | 0 |  | #DIV/0!
245 |  |  |  |  | 0 |  | #DIV/0!
246 |  |  |  |  | 0 |  | #DIV/0!
247 |  |  |  |  | 0 |  | #DIV/0!
248 |  |  |  |  | 0 |  | #DIV/0!
249 |  |  |  |  | 0 |  | #DIV/0!
250 |  |  |  |  | 0 |  | #DIV/0!
251 |  |  |  |  | 0 |  | #DIV/0!
252 |  |  |  |  | 0 |  | #DIV/0!
253 |  |  |  |  | 0 |  | #DIV/0!
254 |  |  |  |  | 0 |  | #DIV/0!
255 |  |  |  |  | 0 |  | #DIV/0!
256 |  |  |  |  | 0 |  | #DIV/0!
257 |  |  |  |  | 0 |  | #DIV/0!
258 |  |  |  |  | 0 |  | #DIV/0!
259 |  |  |  |  | 0 |  | #DIV/0!
260 |  |  |  |  | 0 |  | #DIV/0!
261 |  |  |  |  | 0 |  | #DIV/0!
262 |  |  |  |  | 0 |  | #DIV/0!
263 |  |  |  |  | 0 |  | #DIV/0!
264 |  |  |  |  | 0 |  | #DIV/0!
265 |  |  |  |  | 0 |  | #DIV/0!
266 |  |  |  |  | 0 |  | #DIV/0!
267 |  |  |  |  | 0 |  | #DIV/0!
268 |  |  |  |  | 0 |  | #DIV/0!
269 |  |  |  |  | 0 |  | #DIV/0!
270 |  |  |  |  | 0 |  | #DIV/0!
271 |  |  |  |  | 0 |  | #DIV/0!
272 |  |  |  |  | 0 |  | #DIV/0!
273 |  |  |  |  | 0 |  | #DIV/0!
274 |  |  |  |  | 0 |  | #DIV/0!
275 |  |  |  |  | 0 |  | #DIV/0!
5 | TOTAL FOR THIS SHEET [5] | 0 | 0 | 0 | 0 |  | #DIV/0!
Note on D8: VALUE OF THE DESCRIBED EVENT. INSERT THIS VALUE.
Note on E8: WORK THAT HAS BEEN INSTALLED ON THE SITE. INSERT THIS VALUE
Note on F8: MATERIAL DELIVERED, BUT NOT INSTALLED. 90% OF INVOICE SUBMITTED. INSERT THIS VALUE
Note on G8: WORK INSTALLED AND 90% OF MATERIALS AT THE SITE OR IN STORAGE. CALCUALTED VALUE
Note on I8: AMOUNT OF THE EVENT THAT IS COMPLETED. CALCULATED VALUE

## St Of Cntr Time
FORM DPW – C2 |  |  |  | ='MNTHLY EST'!$J$6
REV 1/05
STATE OF HAWAII
DEPARTMENT OF ACCOUNTING AND GENERAL SERVICES
DIVISION OF PUBLIC WORKS
STATEMENT OF CONTRACT TIME
FOR THE MONTH OF |  |  |  | DECEMBER 2020
PROJECT TITLE | Aliiaimoku Bldg, Replace Air Conditioning System
LOCATION
DAGS JOB NO. | XX-XX-XXXX
MONTH | YEAR | CONTRACT DAYS ELAPSED (Calendar Days) | APPROVED NON-WORK DAYS | COMMENT
JANUARY
FEBRUARY
MARCH
APRIL
MAY
JUNE
JULY
AUGUST
SEPTEMBER
OCTOBER
NOVEMBER
DECEMBER
NOTICE TO PROCEED DATE :
DAYS THIS PERIOD
PREVIOUSLY REPORTED
TOTAL TO DATE |  | 0
ALL LISTED TIME ARE BY CALENDAR DAYS
Date of Notice to Proceed |  |  |  | * All extensions of time shall be previously approved under separate cover before being listed ** Should Actual Work Completed (in %) fall behind Scheduled/Planned Work (in %) by more than 15%, the General Conditions constitute it as being behind schedule. The S-Curve shall be updated and submitted as part of the monthly estimate.
Original Contract Time |  |  | c.d.
*Extensions Granted to Date |  | 0
a. Inclement Weather |  |  | c.d.
b. Change Orders |  |  | c.d.
c. Others |  |  | c.d.
Revised Contract Time |  | 0 | c.d.
Revised Contract Completion Date
Working Days Remaining |  |  | c.d.
** Percent Contract Schedule To Date |  | XX %
**Percent Contract Completed to Date |  | 16.79%
____________________________________ ______________
Contractor's Representative Date
RECOMMEND APPROVAL: |  |  | APPROVED:
______________________________________ ______________ |  |  | ______________________________________ ______________
Project Inspector |  | Date | Chief, Construction Management Branch Date
Internal Use: [ ] Behind Letter to be sent [ ] Change Order Pending [ ] Material Delivery is late [ ] Funding pending
[ ] SEE ATTACHED GRAPH OF TIME VS VALUE [ ] Other:
Note on C30: INSERT NTP DATE
Note on C32: ONLY THOSE THAT HAVE BEEN APPROVED
Note on C37: MUST BE CALCULATED BY HAND
Note on C38: CALCULATE WITH CALENDAR

## Sched Perf.
Project: XXXXXXXXXXXX
DAGS Job No. XX-XX-XX
DATA FOR VERIFICATION OF ON-SCHEDULE PERFORMANCE
MONTH | END OF MONTH / YEAR | SCHEDULED |  |  | ACTUAL |  |  | VARIANCE (I = H-E)
|  | MONTHLY VALUE ( C ) | CUMMULATIVE TOTAL VALUE (D) | TOTAL % COMPLETED ( E ) | MONTHLY VALUE (F) | CUMMULATIVE TOTAL VALUE (G) | TOTAL % COMPLETED (H)
1 | 2022-01-01 | 32107 | 32107 | 3.412% | 27458 | 27458 | 2.918% | -0.4941%
2 | 2022-02-01 | 41596 | 73703 | 7.833% | 35000 | 62458 | 6.638% | -1.195%
3 | 2022-03-01 | 48795 | 122498 | 13.02% | 45219 | 107677 | 11.44% | -1.575%
4 | 2022-04-01 | 53480 | 175978 | 18.7% | 47000 | 154677 | 16.44% | -2.264%
5 | 2022-05-01 | 100000 | 275978 | 29.33% | 55000 | 209677 | 22.28% | -7.046%
6 | 2022-06-01 | 120000 | 395978 | 42.08% | 75000 | 284677 | 30.25% | -11.83%
7 | 2022-07-01 | 130000 | 525978 | 55.9% | 100000 | 384677 | 40.88% | -15.02%
8 | 2022-08-01 | 140000 | 665978 | 70.78% | 230000 | 614677 | 65.32% | -5.452%
9 | 2022-09-01 | 125000 | 790978 | 84.06% | 180000 | 794677 | 84.45% | 0.3931%
10 | 2022-10-01 | 75000 | 865978 | 92.03%
11 | 2022-11-01 | 50000 | 915978 | 97.34%
12 | 2022-12-01 | 25000 | 940978 | 100%
TOTAL CONTRACT AMT. |  | 940978
S-CURVE